Project Work Plan

I. Cover Page

|  | Tracking |  |  |
| --- | --- | --- | --- |

- Assigned by DEC; listed on award letter

- Assigned by the Federal government and are the same for all ARRA 604(b) projects in NYS

- Assigned by DEC and on the Project Summary Fact Sheet.

Sub-recipient

Regional Public Comprehensive Planning Organization or Interstate Organization

| Name |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Federal (IRS) ID# |  |  |  |  |  |  |  |
| D-U-N-S #4 |  |  |  |  |  |  |  |
| Has Federal Central |  |  | X Yes |  |  | □ No |  |
| Congressional | NY-26 |  |  |  |  |  |  |
| District 6 |  |  |  |  |  |  |  |
|  | Organization Contact | Project Manager |  |  | Fiscal Contact |  |  |
| Name |  |  |  |  |  |  |  |
| Street Address |  |  |  |  |  |  |  |
| City, State |  |  |  |  |  |  |  |
| Zip Code +4 |  |  |  |  |  |  |  |
| Telephone |  |  |  |  |  |  |  |
| Fax |  |  |  |  |  |  |  |
| E-mail |  |  |  |  |  |  |  |

- D-U-N-S number is required by ARRA. If your organization does not have a D-U-N-S number, see Dun & Bradstreet website at http://fedgov.dnb.com/webform

- CCR is a federal program to register all organizations that do business with the federal government. Registration is required for ARRA reporting. Detailed information is available at http://www.ccr.gov/FAQ.aspx

- List the Congressional District in which the sub-recipient is located, e.g. NY-26

Pg.1

Project Information

| Project Name | Linus County Stormwater Phase II Comprehensive Plans |
| --- | --- |
| Project Type6 | Phase II Stormwater Planning |

Has a current Regional or Interstate Organization Resolution been submitted?	X Yes  □ No

|  | Project Location(s) |  |
| --- | --- | --- |
| Street Address | N/A |  |
| Municipality7 |  |  |
| Zip Code +4 |  |  |
| County | Linus |  |
| Congressional District | NY-26 |  |
| Waterbody/Watershed | Beautiful River Basin |  |

| Latitude & Longitude | County-wide |
| --- | --- |
| Hydrologic Unit Code | 01010101 |
| (HUC) |  |

- Enter one: TMDL Elements, Green Infrastructure Planning, Phase II Stormwater Planning, or Water Quality Management Planning

- Indicate Town = T, City = C, Village = V plus the name of the municipality

Project Timing and Costs8

| Start Date | January 1, 2010 |
| --- | --- |
| End Date | December 31, 2011 |
| ARRA 604(b) | $100,000 |
| Award Amount |  |
| Total Project Cost | $100,000 |

- Any invoices to be reimbursed must be for services that fall between the start date and completion date of the project. When identifying the proposed start date, make sure it is before work has begun and any costs have been incurred. When identifying the expected completion date, leave yourself enough time to ensure that the project will be completed, final report prepared, and all bills paid within that time period. Give yourself extra time to be sure that all bills will fall within the project schedule to avoid the need for a contract amendment before reimbursement of costs can occur. Do not send any bills or invoices with the workplan.

Pg.2

Linus County Stormwater Phase II Comprehensive Plans

Example Work Plan – Parts IV, VI, VII

IV.  PROJECT OBJECTIVES AND TASKS

| Objective(s) | Task(s)* | Time needed | Responsible Party |
| --- | --- | --- | --- |
|  |  | to Complete |  |
| Encourage consistency of | Develop or obtain a set of principles against which | 10 days | Contractor |
| comprehensive plans and | to compare plans and codes. |  |  |
| municipal codes with low |  |  |  |
|  | Solicit ten (10) municipalities to participate. | 10 days | Project Manager |
| impact development and |  |  |  |
| smart growth principles. | Collect comprehensive plans and municipal codes | 5 days | Contractor |
|  | to review. |  |  |
|  | Conduct Review | 25 days | Project Manager |
|  | Hold follow-up workshop with each municipality. | 30 days | Contractor, Project Manager |
| Complete Reporting as | Prepare Quarterly Reports and submit them to DEC | 24 days | Project Manager |
| Required | by the deadline in the contract. |  |  |
|  | Prepare reimbursement requests using the correct | 24 days | Fiscal Staff |
|  | forms and documentation. |  |  |
|  | Prepare Final Report at end of project and submit | 5 days | Project Manager/Fiscal Staff |
|  | by project end date. |  |  |

- NOTE: Clean Water Act (CWA) Section 604(b) funds are for planning activities only and the project work plan needs to clearly reflect the planning nature of the work to be done under this grant.

Pg.3

VI. DELIVERABLES

List and describe anticipated deliverables associated with tasks identified in Part IV. All segments and/or phases of the project should be included here. Add rows if necessary.

| Tasks* | Anticipated Deliverables |
| --- | --- |
|  | (products and outcomes) |
| Develop or obtain a set of principles against | Contacts with LID and Smart Growth experts. |
|  | Three to four lists of principles. |
| which to compare plans and codes. |  |
|  | Final summary list of principles for use in |
|  | review. |
| Solicit ten (10) municipalities to participate. | List of meetings attended and telephone |
|  | calls/contacts made. |
|  | List of municipalities who will participate. |
| Collect comprehensive plans and municipal | List of comprehensive plans and codes to be |
|  | reviewed. |
| codes to review. |  |
| Conduct Review | Report on each plan or set of codes reviewed. |
| Hold follow-up workshop with each | For each workshop: |
|  | Workshop scope (plan) |
| municipality. |  |
|  | Agenda |
|  | List of attendees |
|  | Summary of outcomes with each municipality. |
| Prepare Quarterly Reports | Eight Quarterly Reports |
| Prepare Reimbursement Requests | Eight Reimbursement Requests |
| Final Report | One Final Report |
| * List tasks identified in Part IV. Objectives and Tasks |  |

Pg.4

|  | VII. PROJECT SCHEDULE |
| --- | --- |
| Task | 2010 |
|  | Jan. Feb. Mar. Apr. May. Jun. Jul. Aug. Sept. Oct. Nov. Dec. |

Develop or obtain a set of principles

against which to compare plans and

codes.

Solicit ten (10) municipalities to

participate.

Collect comprehensive plans and

municipal codes to review.

Conduct Review

Hold follow-up workshop with each

municipality.

Prepare Quarterly Reports

Prepare Reimbursement Requests

Final Report

Pg.5

| Task | 2011 |
| --- | --- |
|  | Jan. Feb. Mar. Apr. May. Jun. Jul. Aug. Sept. Oct. Nov. Dec. |

Develop or obtain a set of principles

against which to compare plans and

codes.

Solicit ten (10) municipalities to

participate.

Collect comprehensive plans and

municipal codes to review.

Conduct Review

Hold follow-up workshop with each

municipality.

Prepare Quarterly Reports

Prepare Reimbursement Requests

Final Report

Pg.6